Department of Computer Science and Engineering

College of Engineering, University of Nevada, Reno

CS 425 Software Engineering

Assignment #2
September 16, 2009
Due: 
Friday, October 2, @ 9:00 p.m. (by email to dascalus@cse.unr.edu, single PDF file named CS425_A2_YourLastName)
Points:  60
Weight in course grade: 5%

1
Do Exercise 4.1, page 91 of the textbook [Ian Sommerville, Software Engineering, 8th Edition, Addison-Wesley 2006]. 






[15 points]
2
Do Exercise 4.9, page 91 of the textbook [Ian Sommerville, Software Engineering, 8th Edition, Addison-Wesley 2005] (100 to 200 words) 




[10 points]
3
Do Exercise 5.2, page 112 of the textbook [Ian Sommerville, Software Engineering, 8th Edition, Addison-Wesley 2005] (100 to 200 words) 



[10 points]
4
The following table sets out a number of activities, durations, and dependencies. Draw an activity network chart and a bar chart showing the project schedule. Indicate the critical path and specify the minimum time required to finish the project.
[25 points]
	Task


	Duration (days)
	Dependencies

	1
	10
	 

	2
	8
	T1

	3
	14
	T1

	4
	10
	T1

	5
	6
	T1 

	6
	10
	T2

	7
	12
	T2

	8
	6
	T3 (M1), T4 (M2)

	9
	12
	T3 (M1), T5 (M3)

	10
	14
	T4 (M2), T5 (M3)

	11
	10
	T6, T7 (M4)

	12
	6
	T9 (M5), T10

	13
	8
	T8, T9 (M5), T10

	14
	10
	T13

	15
	6
	T12 (M7), T14

	16
	8
	T11 (M6), T14

	17
	10
	T15

	18
	14
	T16, T17


Fall 2009

page 1 of 1

